## Sheet1
Date Added | Action | Owner | Status | Date Closed | Comment
2017-06-06 | Sign off on Entity Hierarchy | DP | In progress |  | Minor outstanding points
2017-06-06 | Review of Product Hierarchy | DP | In progress |  | Minor outstanding points
2017-06-16 | Clarify life-cycle approach | AJ | In progress |  | Working assumption that will be in Tradesparent and not source systems. Option exercise not captured as an event so how do we do it for ETD Options. Action get dataset and review
2017-06-27 | Complete on-boarding documentation | IMcK | In progress
2017-06-27 | Close down hosting decision by 15 July | AR | In progress |  | Awaiting on feedback from Ricardo. In progress with Global Security team. Need questionnaire from Maulik. Leaning towards hosted solution assuming can satisfy requirement. Need discussion around support model. Meeting to be set up in White Plains during w/c 24th
2017-07-07 | Tradesparent contract | KB | In progress |  | Progressing well. Minor legal points still outstanding. Decision on hosting required before can be finalised
2017-07-07 | UTI sources | AJ | Not started |  | Set up meeting to confirm UTI source for all external trades (commodity ETD's confirmed but still questions on external FX and commodity OTC
2017-07-07 | Delegated reporting | AJ | Not started |  | What will remain delegated